## Sheet1
Gaziantep Education Project
Project Budget
ID/design |  |  | Labor 1 | Rate | Total | Labor 2 | Rate | Total | M2 | Cost | Materials | Computers | Furniture | Books | Other | Other | Other | Total
Write project concept paper for internal stakeholders (5 pages)
Labor | 480 |  | 32 | 15 | 480 | 0 | 0 | 0 | [9 empty] | 480
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 480 | [15 empty] | 480
Data collection for the four needs (felt/expressed/comparative/normative)
Labor | 320 |  | 128 | 2.5 | 320 | 0 | 0 | 0 | [9 empty] | 320
Other | 80 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 |  |  | 80
Total |  | 400 | [15 empty] | 400
Data analysis, current state: gap assessment analysis and ranking exercise
Labor | 72 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 72 |  |  | 72
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 72 | [15 empty] | 72
Data analysis, future state: report discussing community and organization fit for project
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Develop project intervention logic matrix
Labor | 80 |  | 8 | 10 | 80 | 0 | 0 | 0 | [9 empty] | 80
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 80 | [15 empty] | 80
Write an expression of interest document for potential donors (5 pages)
Labor | 40 |  | 4 | 10 | 40 | 0 | 0 | 0 | [9 empty] | 40
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 40 | [15 empty] | 40
Write project proposal for donor approval (10 pages)
Labor | 720 |  | 90 | 8 | 720 | 0 | 0 | 0 | [9 empty] | 720
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 720 | [15 empty] | 720
Total ID/design |  | 1792
Setup
Recruit project board (3 members; executive/user/supplier perspectives) | [17 empty] | 0 | 1 | 24
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Write project charter (3 pages) | [18 empty] | 1 | 6
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Project launch communication | [18 empty] | 1 | 2
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Risk management: Risk ID/assessment/response planning (risk register) | [18 empty] | 2 | 20
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Total Setup |  | 0
Planning
Write project plan (20 pages) |  |  | 0 | 0 | 0 | 0 | 0 | 0
Labor | 600 |  | 60 | 10 | 600 | 0 | 0 | 0 | [9 empty] | 600
Total |  | 600 | [15 empty] | 600
Total Planning |  | 600
Implementation
Build four primary schools, 200 students each
Construction costs | 620100 | [7 empty] | 1378 | 450 | 620100 | [6 empty] | 620100
Total |  | 620100 | [15 empty] | 620100
Build one secondary school, 400 students
Construction costs | 257850 | [7 empty] | 573 | 450 | 257850 | [6 empty] | 257850
Total |  | 257850 | [15 empty] | 257850
Provide one month training program for 24 primary school teachers and 12 secondary school teachers
Venue | 2600 | [13 empty] | 2600 |  |  | 2600
Trainers | 10400 |  | 104 | 100 | 10400 | [12 empty] | 10400
Supplies | 300 | [13 empty] | 300 |  |  | 300
Refreshments | 3120 | [13 empty] | 3120 |  |  | 3120
Transportation | 1300 | [13 empty] | 1300 |  |  | 1300
Total |  | 17720 | [15 empty] | 17720
Provide supplies: computers, books, furniture
Computers | 15400 | [10 empty] | 15400 | [5 empty] | 15400
Books | 10000 | [12 empty] | 10000 |  |  |  | 10000
Furniture | 50840 | [11 empty] | 50840 |  |  |  |  | 50840
Total |  | 76240 | [15 empty] | 76240
Issues log management
Labor | 1500 |  | 5 | 300 | 1500 | [12 empty] | 1500
Total |  | 1500 | [15 empty] | 1500
HR management (based on staffing plan from “planning” stage):
job descriptions, org charts, recruiting, staff development, performance assessments
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Stakeholder communications: status reports, meetings, trainings
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Stakeholder management: RACI matrix (for the following responsibilities: concept note,
logical framework, project proposal, program plan, budget, implementation, M&E)
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Procurement: ID providers (furniture/computers/supplies), RFPs, negotiation
Labor | 320 |  | 16 | 10 | 160 | 16 | 10 | 160 | [9 empty] | 320
Total |  | 320 | [15 empty] | 320
Logistics: inventory management, transport/storage
N/A
Assets: purchase, administration (furniture/computers/supplies)
Labor | 160 |  | 8 | 10 | 80 | 8 | 10 | 80 | [9 empty] | 160
Total |  | 160 | [15 empty] | 160
Internal controls system
Labor | 160 |  | 8 | 10 | 80 | 8 | 10 | 80 | [9 empty] | 160
Total |  | 160 | [15 empty] | 160
Total Implementation |  | 974050
Monitoring, evaluation and control
Monitoring and evaluation plan (5 pages), addressing the following points:
Labor | 1600 |  | 16 | 100 | 1600 | [12 empty] | 1600 |  |  | 2p | 2d
Total |  | 1600 | [15 empty] | 1600
Monitoring and evaluation activity (construction, procurement/asset management, training)
Research | 50 |  | 5 | 10 | 50 |  |  | 0 | [9 empty] | 50 |  |  | 2 people | 2 weeks | $45/day | $1,080 total
Interviews | 80 |  | 8 | 10 | 80 |  |  | 0 | [9 empty] | 80
Driver | 100 |  | 2 | 50 | 100 |  |  | 0 | [9 empty] | 100
Total |  | 230 | [15 empty] | 230
Risk monitoring process by Project Manager
Project Manager | 0 |  | 16 | 0 | 0 |  |  | 0 | [9 empty] | 0 |  |  | 3d | 2p
Total |  | 0 | [15 empty] | 0
Mid-term evaluation
Labor | 700 |  | 56 | 12.5 | 700 | [12 empty] | 700 |  |  | 2p | 2d
Total |  | 700 | [15 empty] | 700
Final evaluation
Labor | 1500 |  | 120 | 12.5 | 1500 | [12 empty] | 1500 |  |  | 2p | 4d
Total |  | 1500 | [15 empty] | 1500
Sustainable impact evaluation
Labor | 700 |  | 56 | 12.5 | 700 | [12 empty] | 700 |  |  | 2d | 2p
Total |  | 700 | [15 empty] | 700
Total Monitoring, Evaluation and Control |  | 4730
End of project transition
Capacity building for community
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Management of staggered phase-out
N/A
Post-transition support (if applicable)
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
End of project stakeholder meeting
Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Other | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
Total |  | 0 | [15 empty] | 0
Administrative/financial/contractual closure
Labor | 40 |  | 4 | 10 | 40 | [12 empty] | 40
Total |  | 40 | [15 empty] | 40
Capture lessons learned/best practices and After action review
Labor | 40 |  | 4 | 10 | 40 | [12 empty] | 40
Total |  | 40 | [15 empty] | 40
Celebrate
Hotel rental | 300 | [13 empty] | 300 |  |  | 300
Invitations | 150 | [13 empty] | 150 |  |  | 150
Refreshments | 500 | [13 empty] | 500 |  |  | 500
Total |  | 950 | [15 empty] | 950
Total End of Project Transition |  | 1030
Shared Services | [17 empty] | 0
Accounting | [17 empty] | 0
NGO | 25000
Allocation | 10%
Total |  | 2500
Program Manager | [17 empty] | 0
NGO | 40000
Allocation | 10%
Total |  | 4000
Total Shared Services |  | 6500
Total Project Costs |  | 988702