Financial Principles and Project Cost Management
Lecture 6 Activity: Earned Value Analysis

- Estimate percentage completion for each line item of your budget based on the following assumptions:

  - ID/design: 1 month prior to construction, you are two weeks in

  - Setup: 1 month timeframe, you are two weeks in

  - Planning: 2 weeks, you are 10 days in

  - Implementation: 3 months in (4 months construction, teacher training began one week ago)

  - M/E: you are writing the mid-term evaluation now

  - End of project transition: 2 week timeframe, you are 1 week in

- Input the percentages into budget to calculate the earned value for each item

- Receive actual expenditures from each line item from accountant

- Calculate variance as percentage of earned value

  - If >5% over, provide explanation, focusing on whether we can manage remaining expenses to prevent further overspending

  - If >5% under, provide explanation, focusing on how we can ensure the quality of the work has not been compromised