Financial Principles and Project Cost Management
Budget Planning Activity
Work Breakdown Structures

Developing the project budget is a comprehensive process based on multiple work packages, both direct and indirect, for all six phases of project management under the PMD Pro model.  A list of these work packages by project phase is included below.  Each of these work packages includes multiple tasks which need to be reflected in the budget.

We will analyze the following project in developing a comprehensive project management budget:

Build four primary schools (200 students each) and one secondary school (400 students) in Gaziantep, Turkey, provide a one-month teacher training for 24 primary school teachers and 12 secondary school teachers, and provide supplies (computers, books, furniture) for each school
Timeframe: four months for construction, one month for training

In this activity your outcome is to use the work breakdown structure to identify the tasks for each of the project work packages (listed below).  With this information, we will be ready to prepare the project budget.

ID/design

Write project concept paper for internal stakeholders (5 pages)

Data collection for the four needs (felt/expressed/comparative/normative)

Methodology: survey/observation/research in other community/access expert information

Data analysis, current state: gap assessment analysis and ranking exercise

Gap assessment: research in community; where we ARE and where we WANT TO BE

Ranking: select five education needs, rank in importance

Data analysis, future state: report discussing community and organization fit for project

Develop project intervention logic matrix

Write an expression of interest document for potential donors (5 pages)

Write project proposal for donor approval (10 pages)

Setup

Recruit project board (3 members; executive/user/supplier perspectives)

Write project charter (3 pages)

Project launch communication

Risk management: Risk ID/assessment/response planning (risk register)

Planning

Write project plan (20 pages), addressing the following points:

- Scope management: product scope, project scope, work breakdown structures for direct and indirect activities

- Time management: network diagram/critical path

- Project justification management: ID problems, objectives, and the alternatives which the organization can provide

- Stakeholder management: identify the individuals, groups, and institutions which will be affected by the project, and describe their participation/contribution

- Risk management: describe the risk planning completed in during “setup” stage

- Resource management: HR management/staffing plan, project budget (based on the tasks which support the work breakdown packages listed in this activity)

- Coordination: describe how the various stakeholders will work together

Implementation

Build four primary schools, 200 students each

Build one secondary schools, 400 students

Construction costs (including logistics): materials $300/m2, labor $150/m2

Provide one month training program for 24 primary school teachers and 12 secondary school teachers

Provide supplies: computers, books, furniture

Issues log management

HR management (based on staffing plan from “planning” stage): job descriptions, org charts, recruiting, staff development, performance assessments

Stakeholder communications: status reports, meetings, trainings

Stakeholder management: RACI matrix (for the following responsibilities: concept note, logical framework, project proposal, program plan, budget, implementation, monitoring and evaluation)

Procurement: ID providers (furniture/computers/supplies/construction), RFPs, negotiation

Logistics: inventory management, transport/storage

Assets: purchase, administration (furniture/computers/supplies)

Internal controls system

Monitoring, evaluation and control

Monitoring and evaluation plan (5 pages), addressing the following points:

- Indicators, information need, data source, data collection (quantitative or qualitative, cost and complexity)

- Monitoring system: people/resources for collection/review/summary/analysis/feedback for each cycle, data management

Monitoring and evaluation activity (construction, procurement/asset management, training)

Risk monitoring process by Project Manager

Mid-term evaluation (3 pages)

Final evaluation (5 pages)

Sustainable impact evaluation (3 pages)

End of project transition

Capacity building for community

Management of staggered phase-out

Post-transition support (if applicable)

End of project stakeholder meeting

Administrative/financial/contractual closure

Capture lessons learned/best practices

After action review

Celebrate

Shared Services

Accounting

Program Manager