## project budget
Gaziantep Education Project
Project Budget
Earned Value Analysis
|  | Planning Budget |  | Activity Variance | % | $ | Spending Variance | Actual To Date | % Variance | Labor 1 | Rate | Total | Labor 2 | Rate | Total | M2 | Cost | Materials | Computers | Furniture | Books | Other | Other | Total
ID/design
Write project concept paper for internal stakeholders (5 pages)
Labor |  | 480 |  | 0 | 100% | 480 | 24 | 504 | 4.762% | 32 | 15 | 480 | 0 | 0 | 0 | [8 empty] | 480
Total |  |  | 480 | [20 empty] | 480
Data collection for the four needs (felt/expressed/comparative/normative)
Labor |  | 400 |  | 0 | 100% | 400 | -12 | 388 | -3.093% | 128 | 2.5 | 320 | 32 | 2.5 | 80 | [8 empty] | 400
Total |  |  | 400 | [20 empty] | 400
Data analysis, current state: gap assessment analysis and ranking exercise
Labor |  | 72 |  | 0 | 100% | 72 | 7 | 79 | 8.861% | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 72 |  | 72
Total |  |  | 72 | [20 empty] | 72
Data analysis, future state: report discussing community and organization fit for project
Labor |  | 210 |  | 0 | 100% | 210 | 17 | 227 | 7.489% | 14 | 15 | 210 | 0 | 0 | 0 | [8 empty] | 210
Other |  | 140 |  | 0 | 100% | 140 | 6 | 146 | 4.11% | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 50 | 90 | 140
Total |  |  | 350 | [20 empty] | 350
Develop project intervention logic matrix
Labor |  | 80 |  | 0 | 100% | 80 | -2 | 78 | -2.564% | 8 | 10 | 80 | 0 | 0 | 0 | [8 empty] | 80
Total |  |  | 80 | [20 empty] | 80
Write an expression of interest document for potential donors (5 pages)
Labor |  | 40 |  | 0 | 100% | 40 | 0 | 40 | 0% | 4 | 10 | 40 | 0 | 0 | 0 | [8 empty] | 40
Total |  |  | 40 | [20 empty] | 40
Write project proposal for donor approval (10 pages)
Labor |  | 320 |  | 0 | 100% | 320 | -40 | 280 | -14.29% | 40 | 8 | 320 | 0 | 0 | 0 | [8 empty] | 320
Total |  |  | 320 | [20 empty] | 320
Total ID/design |  |  | 1742 | 0 |  | 1742 | 0 | 1742
Setup
Recruit project board (3 members; executive/user/supplier perspectives) | [23 empty] | 0
Other |  | 80 |  | 0 | 100% | 80 | -5 | 75 | -6.667% | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 80 | 80
Total |  |  | 80 | [20 empty] | 80
Write project charter (3 pages)
Labor |  | 240 |  | 0 | 100% | 240 | -10 | 230 | -4.348% | 24 | 10 | 240 | 0 | 0 | 0 | [8 empty] | 240
Total |  |  | 240 | [20 empty] | 240
Project launch communication
Other |  | 840 |  | 0 | 100% | 840 | 30 | 870 | 3.448% | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 840 |  | 840
Total |  |  | 840 | [20 empty] | 840
Risk management: Risk ID/assessment/response planning (risk register)
Labor |  | 200 |  | 0 | 100% | 200 | 20 | 220 | 9.091% | 20 | 10 | 200 | 0 | 0 | 0 | [8 empty] | 200
Total |  |  | 200 | [20 empty] | 200
Total Setup |  |  | 1360 | 0 |  | 1360 | 35 | 1395
Planning
Write project plan (20 pages) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Labor |  | 1200 |  | 0 | 100% | 1200 | -60 | 1140 | -5.263% | 60 | 20 | 1200 | 0 | 0 | 0 | [8 empty] | 1200
Total |  |  | 1200 | [20 empty] | 1200
Total Planning |  |  | 1200 | 0 |  | 1200 | -60 | 1140
Implementation
Internal controls system
Labor |  | 160 |  | 0 | 100% | 160 | 0 | 160 | 0% | 16 | 10 | 160 | 0 | 0 | 0 | [8 empty] | 160
Total |  |  | 160 | [20 empty] | 160
Stakeholder management: RACI matrix (for the following responsibilities: concept note,
logical framework, project proposal, program plan, budget, implementation, M&E)
Labor |  | 100 |  | 0 | 100% | 100 | 0 | 100 | 0% | 5 | 20 | 100 | 0 | 0 | 0 | [8 empty] | 100
Total |  |  | 100 | [20 empty] | 100
Procurement: ID providers (furniture/computers/supplies), RFPs, negotiation
Labor |  | 320 |  | 0 | 100% | 320 | 5 | 325 | 1.538% | 32 | 10 | 320 | 0 | 0 | 0 | [8 empty] | 320
Total |  |  | 320 | [20 empty] | 320
HR management (based on staffing plan from “planning” stage):
job descriptions, org charts, recruiting, staff development, performance assessments
Labor |  | 1200 |  | 0 | 100% | 1200 | 40 | 1240 | 3.226% | 60 | 20 | 1200 | 0 | 0 | 0 | [8 empty] | 1200
Total |  |  | 1200 | [20 empty] | 1200
Issues log management
Labor |  | 400 |  | 0 | 100% | 400 | -10 | 390 | -2.564% | 20 | 20 | 400 | [11 empty] | 400
Total |  |  | 400 | [20 empty] | 400
Stakeholder communications: status reports, meetings, trainings
Labor |  | 400 |  | 0 | 100% | 400 | -15 | 385 | -3.896% | 20 | 20 | 400 | 0 | 0 | 0 | [8 empty] | 400
Total |  |  | 400 | [20 empty] | 400
Logistics: inventory management, transport/storage
N/A
Assets: purchase, administration (furniture/computers/supplies)
Labor |  | 160 |  | 0 | 100% | 160 | 10 | 170 | 5.882% | 16 | 10 | 160 | 0 | 0 | 0 | [8 empty] | 160
Total |  |  | 160 | [20 empty] | 160
Build four primary schools, 200 students each
Construction costs |  | 620100 |  | 0 | 100% | 620100 | -1200 | 618900 | -0.1939% | [6 empty] | 1378 | 450 | 620100 | [5 empty] | 620100
Primaries |  |  | 620100 | [20 empty] | 620100
Build one secondary school, 400 students
Construction costs |  | 257850 |  | 0 | 100% | 257850 | 24150 | 282000 | 8.564% | [6 empty] | 573 | 450 | 257850 | [5 empty] | 257850
Secondaries |  |  | 257850 | [20 empty] | 257850
Provide one month training program for 24 primary school teachers and 12 secondary school teachers
Venue |  | 2600 |  | 0 | 100% | 2600 | 130 | 2730 | 4.762% | [12 empty] | 2600 |  | 2600
Trainers |  | 10400 |  | 0 | 100% | 10400 | -200 | 10200 | -1.961% | 104 | 100 | 10400 | [11 empty] | 10400
Supplies |  | 300 |  | 0 | 100% | 300 | 0 | 300 | 0% | [12 empty] | 300 |  | 300
Refreshments |  | 3120 |  | 0 | 100% | 3120 | 93.6 | 3213.6 | 2.913% | [12 empty] | 3120 |  | 3120
Total |  |  | 16420 | [20 empty] | 16420
Provide supplies: computers, books, furniture
Computers |  | 15400 |  | 0 | 100% | 15400 | 600 | 16000 | 3.75% | [9 empty] | 15400 |  |  |  |  | 15400
Books |  | 10000 |  | 0 | 100% | 10000 | 0 | 10000 | 0% | [11 empty] | 10000 |  |  | 10000
Furniture |  | 50840 |  | 0 | 100% | 50840 | 1260 | 52100 | 2.418% | [10 empty] | 50840 |  |  |  | 50840
Total |  |  | 76240 | [20 empty] | 76240
Total Implementation |  |  | 973350 | 0 |  | 973350 | 24833.6 | 998213.6
Monitoring, evaluation and control
Monitoring and evaluation plan (5 pages)
Labor |  | 200 |  | 0 | 100% | 200 | 0 | 200 | 0% | 16 | 12.5 | 200 | [11 empty] | 200 | 2p | 2d
Total |  |  | 200 | [20 empty] | 200
Monitoring and evaluation activity (construction, procurement/asset management, training)
Research |  | 100 |  | 0 | 100% | 100 | 15 | 115 | 13.04% | 10 | 10 | 100 |  |  | 0 | [8 empty] | 100 | 2 people | 2 weeks | $45/day | $1,080 total
Interviews |  | 100 |  | 0 | 100% | 100 | 10 | 110 | 9.091% | 10 | 10 | 100 |  |  | 0 | [8 empty] | 100
Driver |  | 250 |  | 0 | 100% | 250 | 0 | 250 | 0% | 10 | 25 | 250 |  |  | 0 | [8 empty] | 250
Total |  |  | 450 | [20 empty] | 450
Risk monitoring process by Project Manager
Project Manager |  | 320 |  | 0 | 100% | 320 | 0 | 320 | 0% | 16 | 20 | 320 |  |  | 0 | [8 empty] | 320 | 3d | 2p
Total |  |  | 320 | [20 empty] | 320
Mid-term evaluation
Labor |  | 300 |  | 0 | 100% | 300 | 15 | 315 | 4.762% | 10 | 30 | 300 | [11 empty] | 300 | 2p | 2d
Total |  |  | 300 | [20 empty] | 300
Final evaluation
Labor |  | 900 |  | 0 | 100% | 900 | -20 | 880 | -2.273% | 30 | 30 | 900 | [11 empty] | 900 | 2p | 4d
Total |  |  | 900 | [20 empty] | 900
Sustainable impact evaluation
Labor |  | 300 |  | 0 | 100% | 300 | 20 | 320 | 6.25% | 10 | 30 | 300 | [11 empty] | 300 | 2d | 2p
Total |  |  | 300 | [20 empty] | 300
Total Monitoring, Evaluation and Control |  |  | 2470 | 0 |  | 2470 | 40 | 2510
End of project transition
Capacity building for community
Labor |  | 800 |  | 0 | 100% | 800 | -10 | 790 | -1.266% | 80 | 10 | 800 | 0 | 0 | 0 | [8 empty] | 800
Total |  |  | 800 | [20 empty] | 800
Management of staggered phase-out
N/A
Post-transition support (if applicable)
Labor |  | 1600 |  | 0 | 100% | 1600 | 100 | 1700 | 5.882% | 160 | 10 | 1600 | 0 | 0 | 0 | [8 empty] | 1600
Total |  |  | 1600 | [20 empty] | 1600
End of project stakeholder meeting
Labor |  | 120 |  | 0 | 100% | 120 | 0 | 120 | 0% | 12 | 10 | 120 | 0 | 0 | 0 | [8 empty] | 120
Total |  |  | 120 | [20 empty] | 120
Administrative/financial/contractual closure
Labor |  | 40 |  | 0 | 100% | 40 | 2 | 42 | 4.762% | 4 | 10 | 40 | [11 empty] | 40
Total |  |  | 40 | [20 empty] | 40
Capture lessons learned/best practices and After action review
Labor |  | 120 |  | 0 | 100% | 120 | -20 | 100 | -20% | 12 | 10 | 120 | [11 empty] | 120
Total |  |  | 120 | [20 empty] | 120
Celebrate
Hotel rental |  | 250 |  | 0 | 100% | 250 | 0 | 250 | 0% | [12 empty] | 250 |  | 250
Invitations |  | 150 |  | 0 | 100% | 150 | 15 | 165 | 9.091% | [12 empty] | 150 |  | 150
Refreshments |  | 200 |  | 0 | 100% | 200 | 0 | 200 | 0% | [12 empty] | 200 |  | 200
Total |  |  | 600 | [20 empty] | 600
Total End of Project Transition |  |  | 3280 | 0 |  | 3280 | 87 | 3367
Shared Services | [23 empty] | 0
Accounting | [23 empty] | 0
NGO |  | 25000
Allocation |  | 10%
Total |  |  | 2500
Program Manager | [23 empty] | 0
NGO |  | 40000
Allocation |  | 10%
Total |  |  | 4000
Total Shared Services |  |  | 6500
Total Project Costs |  |  | 989902 | 0 |  | 983402 | 24935.6 | 1014867.6
Project Budget Report
Program Activities
Project ID/design |  |  | 1742 |  |  |  |  | 1742
Project setup |  |  | 1360 |  |  |  |  | 1395
Project planning |  |  | 1200 |  |  |  |  | 1140
Project implementation support activities |  |  | 2740 |  |  |  |  | 2770
School construction, primary |  |  | 620100 |  |  |  |  | 618900
School construction, secondary |  |  | 257850 |  |  |  |  | 282000
Teacher training |  |  | 16420 |  |  |  |  | 16443.6
Computers |  |  | 15400 |  |  |  |  | 16000
Books |  |  | 10000 |  |  |  |  | 10000
Furniture |  |  | 50840 |  |  |  |  | 52100
Monitoring and evaluation |  |  | 2470 |  |  |  |  | 2510
End of project transition |  |  | 3280 |  |  |  |  | 3367
Total Program Activities |  |  | 983402 |  |  |  |  | 1008367.6
Administrative Activities
Shared services
| Accounting | 2500
| Program manager | 4000 | 6500 |  |  |  |  | 6500
Total Administrative Activities |  |  | 6500 |  |  |  |  | 6500
Total Program Budget |  |  | 989902 |  |  |  |  | 1014867.6
Note on AJ32: Thomas Davis: phone, hall
Note on AI38: Thomas Davis: invitations, hall, refreshments
Note on X67: Thomas Davis: monthly
Note on X106: Thomas Davis: I added this in as an allocation estimate for the PM

## budget report template
Gaziantep Education Project
Budget Report
Variance
|  |  | Budget | Actual | $ | % |  | Explanation
Program Activities
Total Program Activities |  |  | 0 | 0 | 0
Administrative Activities
Shared services
| Accounting | 2500
| Program manager | 4000 | 6500 | 6500 | 0 | 0% | -
Total Administrative Activities
Total Program Budget

## budget report
Gaziantep Education Project
Budget Report
Variance
|  |  | Budget | Actual | $ | % |  | Explanation
Program Activities
Project ID/design |  |  | 1742 | 1742 | 0 | 0% | -
Project setup |  |  | 1360 | 1395 | 35 | 2.574% | U
Project planning |  |  | 1200 | 1140 | -60 | -5% | F
Project implementation support activities |  |  | 2740 | 2770 | 30 | 1.095% | U
School construction, primary |  |  | 620100 | 618900 | -1200 | -0.1935% | F
School construction, secondary |  |  | 257850 | 282000 | 24150 | 9.366% | U
Computers |  |  | 15400 | 16000 | 600 | 3.896% | U
Books |  |  | 10000 | 10000 | 0 | 0% | -
Furniture |  |  | 50840 | 52100 | 1260 | 2.478% | U
Teacher training |  |  | 16420 | 16443.6 | 23.6 | 0.1437% | U
Monitoring and evaluation |  |  | 2470 | 2510 | 40 | 1.619% | U
End of project transition |  |  | 3280 | 3367 | 87 | 2.652% | U
Total Program Activities |  |  | 983402 | 1008367.6 | 24965.6 | 2.539% | U
Administrative Activities
Shared services
| Accounting | 2500
| Program manager | 4000 | 6500 | 6500 | 0 | 0% | -
Total Administrative Activities |  |  | 6500 | 6500 | 0 | 0% | -
Total Program Budget |  |  | 989902 | 1014867.6 | 24965.6 | 2.522% | U