## Sheet1
Gaziantep Education Project
Project Budget
Earned Value Analysis
ID/design | Planning Budget |  | Activity Variance | % | $ | Spending Variance | Actual To Date | % Variance | Labor 1 | Rate | Total | Labor 2 | Rate | Total | M2 | Cost | Materials | Computers | Furniture | Books | Other | Other | Total
Write project concept paper for internal stakeholders (5 pages)
Labor | 480 |  | 0 | 100% | 480 | 24 | 504 | 5% | 32 | 15 | 480 | 0 | 0 | 0 | [8 empty] | 480
Total |  | 480 | [20 empty] | 480
Data collection for the four needs (felt/expressed/comparative/normative)
Labor | 400 |  | 0 | 100% | 400 | -12 | 388 | -3% | 128 | 2.5 | 320 | 32 | 2.5 | 80 | [8 empty] | 400
Total |  | 400 | [20 empty] | 400
Data analysis, current state: gap assessment analysis and ranking exercise
Labor | 72 |  | 0 | 100% | 72 | 7 | 79 | 9.722% | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 72 |  | 72
Total |  | 72 | [20 empty] | 72
Data analysis, future state: report discussing community and organization fit for project
Labor | 210 |  | 0 | 100% | 210 | 17 | 227 | 8.095% | 14 | 15 | 210 | 0 | 0 | 0 | [8 empty] | 210
Other | 140 |  | 0 | 100% | 140 | 6 | 146 | 4.286% | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 50 | 90 | 140
Total |  | 350 | [20 empty] | 350
Develop project intervention logic matrix
Labor | 80 |  | 0 | 100% | 80 | -2 | 78 | -2.5% | 8 | 10 | 80 | 0 | 0 | 0 | [8 empty] | 80
Total |  | 80 | [20 empty] | 80
Write an expression of interest document for potential donors (5 pages)
Labor | 40 |  | 0 | 100% | 40 | 0 | 40 | 0% | 4 | 10 | 40 | 0 | 0 | 0 | [8 empty] | 40
Total |  | 40 | [20 empty] | 40
Write project proposal for donor approval (10 pages)
Labor | 320 |  | -320 | 0% | 0 | 0 | 0 | #DIV/0! | 40 | 8 | 320 | 0 | 0 | 0 | [8 empty] | 320
Total |  | 320 | [20 empty] | 320
Total ID/design |  | 1742 | -320 |  | 1422 | 40 | 1462
Setup
Recruit project board (3 members; executive/user/supplier perspectives) | [22 empty] | 0 | 1 | 24
Other | 80 |  | 0 | 100% | 80 | -5 | 75 | -6.25% | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 80 | 80
Total |  | 80 | [20 empty] | 80
Write project charter (3 pages) | [23 empty] | 1 | 6
Labor | 240 |  | -48 | 80% | 192 | -4 | 188 | -2.083% | 24 | 10 | 240 | 0 | 0 | 0 | [8 empty] | 240
Total |  | 240 | [20 empty] | 240
Project launch communication | [23 empty] | 1 | 2
Other | 840 |  | -714 | 15% | 126 | 10 | 136 | 7.937% | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 840 |  | 840
Total |  | 840 | [20 empty] | 840
Risk management: Risk ID/assessment/response planning (risk register) | [23 empty] | 2 | 20
Labor | 200 |  | -170 | 15% | 30 | 0 | 30 | 0% | 20 | 10 | 200 | 0 | 0 | 0 | [8 empty] | 200
Total |  | 200 | [20 empty] | 200
Total Setup |  | 1360 | -932 |  | 428 | 1 | 429
Planning
Write project plan (20 pages) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Labor | 1200 |  | -120 | 90% | 1080 | -86 | 994 | -7.963% | 60 | 20 | 1200 | 0 | 0 | 0 | [8 empty] | 1200
Total |  | 1200 | [20 empty] | 1200
Total Planning |  | 1200 | -120 |  | 1080 | -86 | 994
Implementation
Internal controls system
Labor | 160 |  | 0 | 100% | 160 | 0 | 160 | 0% | 16 | 10 | 160 | 0 | 0 | 0 | [8 empty] | 160
Total |  | 160 | [20 empty] | 160
Stakeholder management: RACI matrix (for the following responsibilities: concept note,
logical framework, project proposal, program plan, budget, implementation, M&E)
Labor | 100 |  | 0 | 100% | 100 | 0 | 100 | 0% | 5 | 20 | 100 | 0 | 0 | 0 | [8 empty] | 100
Total |  | 100 | [20 empty] | 100
Procurement: ID providers (furniture/computers/supplies), RFPs, negotiation
Labor | 320 |  | -32 | 90% | 288 | 14.4 | 302.4 | 5% | 32 | 10 | 320 | 0 | 0 | 0 | [8 empty] | 320
Total |  | 320 | [20 empty] | 320
HR management (based on staffing plan from “planning” stage):
job descriptions, org charts, recruiting, staff development, performance assessments
Labor | 1200 |  | -240 | 80% | 960 | -19.2 | 940.8 | -2% | 60 | 20 | 1200 | 0 | 0 | 0 | [8 empty] | 1200
Total |  | 1200 | [20 empty] | 1200
Issues log management
Labor | 400 |  | -200 | 50% | 200 | 0 | 200 | 0% | 20 | 20 | 400 | [11 empty] | 400
Total |  | 400 | [20 empty] | 400
Stakeholder communications: status reports, meetings, trainings
Labor | 400 |  | -240 | 40% | 160 | -8 | 152 | -5% | 20 | 20 | 400 | 0 | 0 | 0 | [8 empty] | 400
Total |  | 400 | [20 empty] | 400
Logistics: inventory management, transport/storage
N/A
Assets: purchase, administration (furniture/computers/supplies)
Labor | 160 |  | -112 | 30% | 48 | 3.84 | 51.84 | 8% | 16 | 10 | 160 | 0 | 0 | 0 | [8 empty] | 160
Total |  | 160 | [20 empty] | 160
Build four primary schools, 200 students each
Construction costs | 620100 |  | -124020 | 80% | 496080 | -9921.6 | 486158.4 | -2% | [6 empty] | 1378 | 450 | 620100 | [5 empty] | 620100
Total |  | 620100 | [20 empty] | 620100
Build one secondary school, 400 students
Construction costs | 257850 |  | -51570 | 80% | 206280 | 24753.6 | 231033.6 | 12% | [6 empty] | 573 | 450 | 257850 | [5 empty] | 257850
Total |  | 257850 | [20 empty] | 257850
Provide one month training program for 24 primary school teachers and 12 secondary school teachers
Venue | 2600 |  | 0 | 100% | 2600 | 130 | 2730 | 5% | [12 empty] | 2600 |  | 2600
Trainers | 10400 |  | -7280 | 30% | 3120 | 0 | 3120 | 0% | 104 | 100 | 10400 | [11 empty] | 10400
Supplies | 300 |  | 0 | 100% | 300 | 0 | 300 | 0% | [12 empty] | 300 |  | 300
Refreshments | 3120 |  | 0 | 100% | 3120 | 93.6 | 3213.6 | 3% | [12 empty] | 3120 |  | 3120
Total |  | 16420 | [20 empty] | 16420
Provide supplies: computers, books, furniture
Computers | 15400 |  | -10780 | 30% | 4620 | 0 | 4620 | 0% | [9 empty] | 15400 |  |  |  |  | 15400
Books | 10000 |  | -7000 | 30% | 3000 | 240 | 3240 | 8% | [11 empty] | 10000 |  |  | 10000
Furniture | 50840 |  | -35588 | 30% | 15252 | 0 | 15252 | 0% | [10 empty] | 50840 |  |  |  | 50840
Total |  | 76240 | [20 empty] | 76240
Total Implementation |  | 973350 | -237062 |  | 736288 | 15295.6 | 749667.6
Monitoring, evaluation and control
Monitoring and evaluation plan (5 pages)
Labor | 200 |  | -60 | 70% | 140 | 0 | 140 | 0% | 16 | 12.5 | 200 | [11 empty] | 200 |  |  | 2p | 2d
Total |  | 200 | [20 empty] | 200
Monitoring and evaluation activity (construction, procurement/asset management, training)
Research | 100 |  | -40 | 60% | 60 | -1.2 | 58.8 | -2% | 10 | 10 | 100 |  |  | 0 | [8 empty] | 100 |  |  | 2 people | 2 weeks | $45/day | $1,080 total
Interviews | 100 |  | -50 | 50% | 50 | 6 | 56 | 12% | 10 | 10 | 100 |  |  | 0 | [8 empty] | 100
Driver | 250 |  | -125 | 50% | 125 | 6.25 | 131.25 | 5% | 10 | 25 | 250 |  |  | 0 | [8 empty] | 250
Total |  | 450 | [20 empty] | 450
Risk monitoring process by Project Manager
Project Manager | 320 |  | -208 | 35% | 112 | 0 | 112 | 0% | 16 | 20 | 320 |  |  | 0 | [8 empty] | 320 |  |  | 3d | 2p
Total |  | 320 | [20 empty] | 320
Mid-term evaluation
Labor | 300 |  | -180 | 40% | 120 | -7.2 | 112.8 | -6% | 10 | 30 | 300 | [11 empty] | 300 |  |  | 2p | 2d
Total |  | 300 | [20 empty] | 300
Final evaluation
Labor | 900 |  | -900 | 0% | 0 | 0 | 0 | #DIV/0! | 30 | 30 | 900 | [11 empty] | 900 |  |  | 2p | 4d
Total |  | 900 | [20 empty] | 900
Sustainable impact evaluation
Labor | 300 |  | -300 | 0% | 0 | 0 | 0 | #DIV/0! | 10 | 30 | 300 | [11 empty] | 300 |  |  | 2d | 2p
Total |  | 300 | [20 empty] | 300
Total Monitoring, Evaluation and Control |  | 2470 | -1863 |  | 607 | 3.85 | 610.85
End of project transition
Capacity building for community
Labor | 800 |  | -80 | 90% | 720 | -14.4 | 705.6 | -2% | 80 | 10 | 800 | 0 | 0 | 0 | [8 empty] | 800
Total |  | 800 | [20 empty] | 800
Management of staggered phase-out
N/A
Post-transition support (if applicable)
Labor | 1600 |  | -1600 | 0% | 0 | 0 | 0 | #DIV/0! | 160 | 10 | 1600 | 0 | 0 | 0 | [8 empty] | 1600
Total |  | 1600 | [20 empty] | 1600
End of project stakeholder meeting
Labor | 120 |  | -120 | 0% | 0 | 0 | 0 | #DIV/0! | 12 | 10 | 120 | 0 | 0 | 0 | [8 empty] | 120
Total |  | 120 | [20 empty] | 120
Administrative/financial/contractual closure
Labor | 40 |  | -32 | 20% | 8 | 0.08 | 8.08 | 1% | 4 | 10 | 40 | [11 empty] | 40
Total |  | 40 | [20 empty] | 40
Capture lessons learned/best practices and After action review
Labor | 120 |  | -108 | 10% | 12 | 0.84 | 12.84 | 7% | 12 | 10 | 120 | [11 empty] | 120
Total |  | 120 | [20 empty] | 120
Celebrate
Hotel rental | 250 |  | -150 | 40% | 100 | 0 | 100 | 0% | [12 empty] | 250 |  | 250
Invitations | 150 |  | -150 | 0% | 0 | 0 | 0 | #DIV/0! | [12 empty] | 150 |  | 150
Refreshments | 200 |  | -200 | 0% | 0 | 0 | 0 | #DIV/0! | [12 empty] | 200 |  | 200
Total |  | 600 | [20 empty] | 600
Total End of Project Transition |  | 3280 | -2440 |  | 840 | -13.48 | 826.52
Shared Services | [22 empty] | 0
Accounting | [22 empty] | 0
NGO | 25000
Allocation | 10%
Total |  | 2500
Program Manager | [22 empty] | 0
NGO | 40000
Allocation | 10%
Total |  | 4000
Total Shared Services |  | 6500
Total Project Costs |  | 989902 | -242737 |  | 740665 | 15240.97 | 753989.97
Note on AJ31: Thomas Davis: phone, hall
Note on AI37: Thomas Davis: invitations, hall, refreshments
Note on X66: Thomas Davis: monthly
Note on X105: Thomas Davis: I added this in as an allocation estimate for the PM