Financial Principles and Project Cost Management
Course Project

DUE DATE:  Saturday 4 March 2017, 5pm via email (tomas.davis@hotmail.com)

You are working on the following project:

Construct a 600m2 building in Hargeisa to be a small business incubator, providing free office space for 30 entrepreneurs for six months as well as a one-month entrepreneur “boot camp” with training in marketing, management, accounting, and finance

Your budget includes the following work packages by project phase:

ID/design

- Data collection and analysis

- Project intervention logic matrix

- Project proposal

Setup

- Recruit 3-member board

- Project charter

- Risk register

Planning

- Project plan

Implementation

- HR management

- Building construction (using a general contractor)

- Building equipment

- Boot camp training program

Monitoring, evaluation and control

- Monitoring and evaluation activity

- Mid-term evaluation

- Final evaluation

End of project transition

- Post-transition support

- End of project stakeholder meeting

- Celebrate

Shared services

- Accounting/finance (NGO annual budget amount is $80,000, your project uses 5% of these services)

You have received a top-down budget allocation of $500,000.  At the end of the project, you have spent $560,000.

REQUIRED:

- Project budget organized by project phase showing budget, actual, and variance (based on your professional judgement as a project manager, you will decide the amounts you budget and the amounts you actually spend); you do not need to complete EVA analysis, as the project is now 100% complete

- Budget report organized by “Program activities” and “Administrative activities” showing budget, actual, variance ($ and %), favorable/unfavorable, and explanations for all differences

- Templates for both reports are provided at the course website