Project Management Fundamentals
Lecture Three Exercises SAMPLE

Continue with the project management project you selected from the scenarios below:

- Malaria eradication in Togo

- Reintegration program for ex-militants in Colombia

- Financial literacy program for the poor in Bangladesh

- Microentrepreneurship program in India

- Job placement program for professional Syrian refugees relocating to Canada

Based on your ideas regarding the project, complete the following activities:

- Describe how the governance concepts of accountability and authority relate to your project.

  - Accountability: project manager, program manager, community organization administrator, leadership expert

  - Authority: PM – select participants, spending authority up to 3% over budget, individual transactions up to $100; if more than 50% of participants do not complete first semester of program, program management passes to board

- Create a three-member board and provide background information for each of the members.

  - Experienced community organization administrator; university student who is the project “champion” at his/her university; individual with organizational leadership/leadership training experience

- Write a project charter covering the key ideas and parameters of your project.

Purpose: provide leadership training to university students and connect the students to meaningful and lasting community service projects
Activities: 1 hour weekly community service and 2 hour monthly leadership training session; 6 male students, 6 female students, 1 program director, 1 program coordinator

Schedule: January – select one university for student recruiting; January/February – select participating students; February – identify training facility, begin leadership training program, visit/evaluate community organizations; March – begin community service project and community service training; May – reception for students, parents, and community organization administrator; end of May – evaluation of program/decision gate to continue/change/end

Budget: supplies for community organization = SLS100,000-150,000/month

Tolerances: up to 50% of students leave the program during first semester; beyond that, board has authority to seek new participants or to discontinue program

Risks: participants leave program, no buy-in from parents, inability to identify appropriate community service activity, inadequate training, scheduling/attendance issues

Assumptions: students will attend leadership training sessions, sessions will be effective, students will participate in community service project, community service will provide meaningful benefit to community

Constraints: time constraints of all participants relating to volunteer activity (time), leadership trainers (resources), number of participating students and number of community organizations which can be effectively served through the program (scope)

- Identify three potential risks to your project and create a risk register to assess the probability and impact of each risk, and decide how to respond to each risk; avoid/transfer/reduce/accept.

Priority risks, high/high
Students leave program – ensure students understand program is a personal commitment, emphasize importance of community service and connection to Somaliland Vision 2030, provide high quality leadership training for the students

Ineffective training – provide adequate training for students through “on the job” participation in community service in an assistant role, provide easy access to program director and program coordinator by phone, director and/or coordinator on site during community organization visits

High impact/low risk – contingency plan for identifying new community organizations

Low impact/high probability, low/low – monitor in the event these risks become more significant