Project Management Fundamentals
Lecture Four Exercises SAMPLE

Based on your ideas regarding the project, complete the following activities:

- Define the product scope as well as the project scope of your project.

Product: leadership training for university students and community service by university students.

Project: recruit and train 12 students (community service skills and leadership), select community organization, for one semester pilot project, possible two year full project

- Develop a work breakdown structure graph for your project, including at least three work packages and at least three tasks for each work package.

- Sequence the tasks of each of your work packages from activity 2) and structure these tasks into a network diagram showing the critical path of each work package.

SEE DIAGRAM AT END OF DOCUMENT

- Create a bottom-up budget for your project including detailed estimates for the work packages from activity 2).  Include all direct activities, at least two indirect activities (one of which should be monitoring and evaluation), and at least one shared service allocation estimate.

- Select one of the work package budgets from activity 4).  Assume that your organization uses top-down budgeting, and the amount you have been allocated for direct costs for this work package is 15% less than the amount of your estimate.  Revise your budget so that the new total direct costs amount matches the allocation you have been given in the top-down budget.

3)

The gray boxes represent the critical path; the yellow boxes represent precedents; they must happen to enable progress to continue in another activity; the arrows lead from the precedent to the dependent activity; the dependent activity cannot happen until the precedent activity occurs.

Precedents: students must be invited before participating in training (logical), and training must begin before community service (program requirement).