Project Management Fundamentals
Lecture Seven Exercises SAMPLE

Continue with the project management project you selected from the scenarios below:

- Malaria eradication in Togo

- Reintegration program for ex-militants in Colombia

- Financial literacy program for the poor in Bangladesh

- Microentrepreneurship program in India

- Job placement program for professional Syrian refugees relocating to Canada

Based on your ideas regarding the project, complete the following activities:

- Use the monitoring and evaluation plan template to identify data and information requirements and frequency of your monitoring activities.

- Describe one qualitative and one quantitative data collection tool to obtain the information you need for your monitoring activities.

Qualitative: beneficiary and volunteer interviews – to evaluate effectiveness of program in developing positive volunteer/beneficiary relationships and to investigate below-expected results

Quantitative: percentage participation – to determine participation rate of volunteers and to compare to expected rate and investigate below-expected participation

- Create a schedule and budget for one cycle of your monitoring activities.

- Complete a final evaluation of your project based on the four evaluation questions included in the presentation.  Assume all answers are “yes”; provide a description of your evaluation results.

Desired outcomes: 80% of beneficiaries and 80% of volunteers indicated “favorable” or “very favorable” results from participation in program

Relevant, effective, and efficient:
Relevant: community service provides a meaningful contribution to members of society with limited resources and/or special needs, and provides an effective opportunity for university students to contribute to the community and to develop a spirit of volunteerism

Effective: project produced the desired outcome – a high level of beneficiary and volunteer satisfaction which contributes to the goal of enabling society to meet needs without reliance on government

Efficient: project provided service to six community organizations with 60 university volunteers with a total budget of $2,000

Sustainability: a local program director has been hired, a systematic leadership training program is in place, four university relationships have been established for volunteer recruiting, and strong relationships have been developed with six community organizations; ongoing expense is salary of program manager of $500/month, which has been funded by Ministry of Education for the following 12 months

Assumptions: valid – recruitment led to community service, community service led to positive volunteer/beneficiary relationships, positive volunteer/beneficiary relationships contribute to increased confidence and personal well-being

- Perform a sustainable impact evaluation for your project one year after end of project transition.  Assume the evaluation is favorable; provide a description of your evaluation results.

One year after transition, Leadership Hargeisa continues to operate.  The same program director is in place, six universities are participating, and 100 university students currently participate in weekly community service.  For ongoing funding for the program, the program manager is discussing sponsorship with local employers in the event the Ministry of Education does not continue to provide support.