Project Management Fundamentals
Lecture Eight Exercises SAMPLE

Continue with the project management project you selected from the scenarios below:

- Malaria eradication in Togo

- Reintegration program for ex-militants in Colombia

- Financial literacy program for the poor in Bangladesh

- Microentrepreneurship program in India

- Job placement program for professional Syrian refugees relocating to Canada

Based on your ideas regarding the project, complete the following activities:

- Assume that you have the opportunity to expand your project; provide a description of the expanded project scope.

Ministry of Education has requested a university student community service for Amoud University in Borame; 12 male/12 female students, travel arrangements for leadership trainer, introductions to community organizations.

- Describe the qualities of a local partner you will select to take responsibility for the continuation of the project after transition.

Program coordinator is a Somalilander, is developing expertise with the program, has good student and community organization relationships, and is willing to perform the role of Project Manager.

- Describe a two-phase staggered phase-out which will maximize the effectiveness of the project transition to the local community.

Phase one: hand off of community service project management to local Program Manager.

Phase two: end of project transition of leadership training program to local Program Manager.

- Describe the deliverables you envision presenting to the donor.

- Established community service program with committed participating university students and community organizations

- Trained local Program Manager to continue program

- 35 students completing one-year program, 24 students completing first semester of one-year program, and 24 students entering program; established community service projects with six community organizations

- Complete the following comment from a community member at the end of project stakeholder meeting: “Beyond the technical achievements of the project, we especially value __________________________________________________________________.”

“…having a group of university students with a committed spirit of volunteerism and contribution.  This presence enhances the quality of our community and these students provide role models for our secondary school students.”

- Create a closure checklist to address one task in each of the categories of administrative, financial, and contractual closure.

Administrative
Promote Project Coordinator to Program Director

Financial
Ensure payment of any outstanding expenditures (payroll, supplies) relating to program

Contractual
Receive signed acknowledgment of receipt of deliverables from donor

- Complete an after action review which addresses the five questions regarding project outcomes.

What did we set out to do?

Develop a community service and leadership training program with 48 university students in Hargeisa providing community service to four community organizations.

What did we achieve?

35 students completed program, 48 students current participating in program, serving six community organizations.

What went really well?

The volunteers were enthusiastic about the opportunity to participate in community service.
The community organization beneficiaries enjoyed the opportunity to engage directly with volunteer university students.

What could have gone better?
Our success in engaging community organizations was limited, and more community organization participation might create a more successful program.

What can we learn from this project?
The concept of community service is a valuable concept in the eyes of the community and can produce meaningful contribution to society.

University students are valuable assets for participation in community service projects, want to contribute to their societies, and have a desire and ability to learn and develop leadership skills.

Community organization connection and dialogue is an important part of establishing a successful community service program.