Project Management Fundamentals
Lecture One Exercises SAMPLE

Select one of the project management scenarios below:

- Malaria eradication in Togo

- Reintegration program for ex-militants in Colombia

- Financial literacy program for the poor in Bangladesh

- Microentrepreneurship program in India

- Job placement program for professional Syrian refugees relocating to Canada

Based on your ideas regarding the project, complete the following activities:

- Provide two examples each of project management constraints:

  - Resources: money, tutoring facility

  - Scope: number of mentors available, number of school directors to support program

  - Time: volunteer time availability, time constraint to complete project in two years

- Describe how the six development specific factors of project management relate to your project.

Social goals: the goal is to create self-confidence and academic opportunity for students

Complex problems: underdeveloped education system

Challenging contexts: limited education resources create challenges for students

Complex relationships: students/mentors/parents/school director/Ministry of Education

Participatory: ask students, parents, school director what their needs are

Transfer of learning: train a local program director to manage project at transition

- Describe how the five project management principles apply to your project.

Balanced: design/planning/setup/implementation/MEC/transition all require equal effort

Comprehensive: management disciplines of scope (number of participants), time (two year project involving several time constrained tasks), resources (mentors), risk (participants leave program, program does not result in academic improvement), project justification (underdeveloped education is a real problem which justifies this project), stakeholders (communicate with and understand the needs of students, parents, schools, and mentors)

Integrated: connection among the 6 project management phases

Participatory: ask students, parents, school director what their needs are

Iterative: as information/insight is obtained, adjust project as needed

- Describe how the four project manager competencies will affect your project.

Technical: ability to execute the six phases of project management

Leadership: ability to support and inspire mentors and students

Self-discipline: ability to stay committed to project and be consistent in performance

Development sector: understanding and successfully working with the development specific project management factors (social/problems/context/relationships/participatory/learning)

- Provide two examples of application of the project management disciplines to your project (lecture one only provides a list of these without details; use your judgment here).

Resource management: being able to develop an accurate, detailed budget and then work effectively within these resource limits

Stakeholder management: communicating with and understand the needs of students, parents, schools, and mentors, requesting their participation/feedback in project design, setup, and planning