Project Management Fundamentals
Lecture Three Exercises

Continue with the project management project you selected from the scenarios below:

- Malaria eradication in Togo

- Reintegration program for ex-militants in Colombia

- Financial literacy program for the poor in Bangladesh

- Microentrepreneurship program in India

- Job placement program for professional Syrian refugees relocating to Canada

Based on your ideas regarding the project, complete the following activities:

- Describe how the governance concepts of authority and accountability relate to your project.

- Create a three-member board and provide background information for each of the members.

- Write a project charter covering the key ideas and parameters of your project.

- Identify three potential risks to your project and create a risk register to assess the probability and impact of each risk, and decide how to respond to each risk; avoid/transfer/reduce/accept.