Project Management Fundamentals
Lecture Five Exercises SAMPLE

Continue with the project management project you selected from the scenarios below:

- Malaria eradication in Togo

- Reintegration program for ex-militants in Colombia

- Financial literacy program for the poor in Bangladesh

- Microentrepreneurship program in India

- Job placement program for professional Syrian refugees relocating to Canada

Based on your ideas regarding the project, complete the following activities:

- Describe two issues that might occur during the project which could be resolved on site.

Students or mentors late for tutoring session; mentor calls student or student calls mentor, when more than one session is occurring at same time participants can form “groups” until late party arrives.

Student does not have classwork for tutoring session; mentor can propose alternative content for the session relevant to the usual tutoring content.

- Identify two issues that might occur which would require your attention as the project manager.  Create an issue log include a description of the issue and who the issue should be assigned to for resolution.

- Write job descriptions for three project staff you will need to hire for your project.

Tutoring Trainer: lead a 6-hour training program for mentors participating in the program; academic experience as teacher or tutor

Program Coordinator: coordinate schedules of mentor/student pairs, confirm participation and facilities availability one day before session via SMS; 6 months experience in small project administration

M&E Data Analyst: collect student performance data for ongoing monitoring, interim evaluations (end of semester) to assess actual outcomes vs. planned outcomes, and final evaluation (two years) to assess overall project outcomes; 6 months M&E experience OR undergraduate degree in development studies or similar field

- Create an organization chart for a six-member project management team, using your judgment to determine team member roles and reporting relationships.

- Outline a half-day training program which would be appropriate for your team.

9:00AM – arrival
9:15AM – welcome from Program Director

9:30AM – mentor introductions; university, major, why participating in program

10:00AM – group training, qualities of a successful mentor (Tutoring Trainer)

10:30AM – mentor role plays (led by Program Director)
11:00AM – discussion, mentoring challenges (led by Tutoring Trainer)

11:30AM – leadership training (Program Director)

12:00PM – end of training

- Write a status report describing your project halfway to completion.

The project has completed its first year of the two-year project timeframe.  During the first semester, 10 mentor/student pairs joined the program, and we organized a training for new mentors before the beginning of the program.  All ten groups completed the first semester.  During the second semester, 8 of the original mentors continued the program, 7 of the original students continued the program, and we recruited an additional 12 mentors from a second university and 13 students from the same secondary to expand the program to 20 mentor/student pairs.  We opened the second semester with a training for new mentors.  At the end of the second semester, 16 mentors and 14 students indicated their desire to continue in the program during the following semester.  Our budget for the first year was $800, and we were 6% under budget with actual expenditure of $752.

- Create a RACI matrix for two direct tasks and one administrative task relating to your project.

- Identify a product you will need to purchase (building materials, inventory, computers, etc.) and list four criteria (one should be price) you will evaluate in your evaluation of supplier proposals.

Computer: price, local availability, setup assistance, references/reputation

- Select two categories of controls from the internal controls checklist and provide information to address the questions asked in each category.

Human resources
Documented HR policies providing procedures for recruiting, performance review, promotion, and termination are available
project employees complete monthly report describing dates/description of project activities

Financial
Petty cash is controlled by the program coordinator; expenses are approved by the program director; checks are signed by program director and organization finance officer; bank reconciliations are prepared by organization finance officer; financial statements are prepared by organization accounting department; adequate segregation of duties (authorization/custody/reconciliation/accounting) are in place