Project Management Fundamentals
Lecture Eight Exercises

Continue with the project management project you selected from the scenarios below:

- Malaria eradication in Togo

- Reintegration program for ex-militants in Colombia

- Financial literacy program for the poor in Bangladesh

- Microentrepreneurship program in India

- Job placement program for professional Syrian refugees relocating to Canada

Based on your ideas regarding the project, complete the following activities:

- Assume that you have the opportunity to expand your project; provide a description of the expanded project scope.

- Describe the qualities of a local partner you will select to take responsibility for the continuation of the project after transition.

- Describe a two-phase staggered phase-out which will maximize the effectiveness of the project transition to the local community.

- Describe the deliverables you envision presenting to the donor.

- Complete the following comment from a community member at the end of project stakeholder meeting: “Beyond the technical achievements of the project, we especially value __________________________________________________________________.”

- Create a closure checklist to address one task in each of the categories of administrative, financial, and contractual closure.

- Complete an after action review which addresses the five questions regarding project outcomes.